## INSTRUCTIONS
Welcome to WELL!
Instructions How to use these checklists to set goals, identify opportunities, review progress and celebrate achievements
Checklists
The checklists included here can be used throughout onboarding and subscription for clients and organizations applying WELL at scale. Each checklist focuses on a specific step in the process, highlighting key tasks and activities for setting goals and keeping your team on track. Contents: • Goals and strategy setting • Getting started - Month 1 • Getting started - Month 2 • Team onboarding • WELL assessment • Preparing documentation • Review cycle(s) • Submitting documentation • Preparing for performance testing (optional) • Responding to preliminary review comments • Celebrating achievements • Integrating WELL into CSR / ESG reporting • Celebrating - PR and employee / tenant engagement • Renewal planning • Preparing for your WELL renewal • Setting your annual WELL goals and plan
Checklist instructions
1. Make a copy of this document by going to File > Make a copy. 2. This document includes multiple tabs with suggested action items for each stage of your WELL journey. 3. Add tasks to capture additional steps in the checklist as needed and customize the point person for each task. 4. Add notes and relevant links wherever needed to document tasks, progress, and additional detail. 5. Share this document with members of your team. Use these checklists during check-ins with your team and with your WELL coaching contact. Share these checklists with other members of your team, relevant consultants, etc. to track key tasks, roles and responsibilities, and progress.

## Getting started - Month 1
Action item | Point person | Status | Notes/questions | Links/Resources
Join welcome call with your WELL coaching contact | Coaching contact to set up
Identify your WELL team - consultant (if applicable), HR, sustainability, facilities, real estate, marketing, etc. and add to the Team tab in your dashboard | Administrator |  |  | Add, modify or remove team members in the WELL project dashboard
Complete the WELL survey (optional) to suggest features to target | Administrator |  |  | Completing your WELL scorecard
Finalize the locations being subscribed to WELL | Administrator
Upload your locations into the WELL dashboard | Administrator
Review the WELL goals module sent from your coaching contact | Administrator |  | Coaching contact will email
Invite your WELL team to your onboarding call | Administrator |  | Coaching contact will set up the onboarding call
Sign your WELL agreement | Owner |  |  | https://account.wellcertified.com/

## Getting started - Month 2
Action item | Point person | Status | Notes/questions | Links/Resources
Join an onboarding call with your WELL team and coaching contact | Coaching contact to set up
Start your WELL assessment (see WELL assessment tab) | Administrator
Review the WELL Guidebook | Administrator
Share your WELL goals and plan with your leadership and WELL team (optional) | Administrator
Talk with your PR/Communications staff about publicizing your WELL engagement (optional) | Administrator |  |  | Marketing Guidelines (Achievement) Marketing Guidelines (Subscription)
Review WELL PR and engagement materials (optional) | PR rep |  |  | Marketing Guidelines
Complete your Profile tab in your WELL dashboard (optional) | PR rep |  |  | How to complete your project profile

## WELL assessment
Action item | Point person | Status | Notes/questions | Links/Resources
Assign your WELL team to assess targeted features | Administrator |  | Add people to your Team tab in your dashboard for access | Completing your WELL scorecard
Review the WELL scorecard and finalize the 'yes' features for first review cycle | Administrator
Finalize plans for your review, including any targeted achievements and features you'll be submitting | Administrator
Finalize target date for your review submission | Administrator |  |  | How to update your documentation submission date

## Preparing documentation
Action item | Point person | Status | Notes/questions | Links/Resources
Review the WELL documentation guide | Administrator |  |  | WELL documentation guide
Review sample documentation in the Resources tab | Administrator |  |  | https://account.wellcertified.com/
Review template Letters of Assurance to identify who is signing each one in the Scorecard | Administrator |  |  | https://account.wellcertified.com/
Assemble documents from your team | Administrator |  |  | Boosting your WELL achievement with shareable documents
Create any missing documents that are needed | Administrator
Annotate and translate documents as needed to highlight relevant info | Administrator |  |  | WELL annotation guide
Review your Locations tab to ensure all info is correct and occupancy is listed for each property | Administrator |  |  | https://account.wellcertified.com/
Confirm your WELL agreement is signed | Administrator |  |  | https://account.wellcertified.com/

## Submitting documentation
Action item | Point person | Status | Notes/questions | Links/Resources
Upload documents to your dashboard | Administrator |  |  | Uploading your WELL documentation article
Assign documents to locations where they apply | Administrator |  |  | Uploading your WELL documentation article
Identify any features pursued that require audited documents | Administrator |  | Audit locations are identified when you assign a document to locations pursuing that feature part | Your guide to WELL at scale documentation review
Submit for review | Administrator |  |  | Submitting your WELL documentation article

## Preparing for performance testi
Action item | Point person | Status | Notes/questions | Links/Resources
Identify the performance testing features being targeted this year (note as yes in your scorecard) | Administrator |  |  | Performance Testing Guide
Contact IWBI by emailing PVscheduling@wellcertified.com, and we can match with you an available WELL Performance Testing Organization OR Contract directly with an approved WELL Performance Testing Organization | Administrator |  |  | Hire a Performance Testing Agent
Finalize a date for performance testing | Administrator, with PT Agent
Provide any materials required to your Performance Testing Agent | Administrator, with PT Agent |  | Include representative floor plans, performance testing features and options being pursued, etc.
Add your Performance Testing Agent to your Team tab | Administrator |  |  | https://account.wellcertified.com/
Hold prep call with your Performance Testing Agent | PT Agent
Prep for performance testing using the Performance Verification punch list | Administrator |  |  | Performance Verification punch list tool
Participate on-site during the performance testing | Administrator |  |  | Planning for performance testing
Performance Testing Organization submits passing results (20-25 day business review, with up to 2 rounds of review) | PT Agent |  | Only data that meets the required WELL thresholds needs to be submitted for review.

## Responding to preliminary revie
Action item | Point person | Status | Notes/questions | Links/Resources
View your review sheet | Administrator |  |  | https://account.wellcertified.com/
Identify any documentation that needs to be added or edited | Administrator
Review the article 'Responding to preliminary review comments' | Administrator |  |  | Responding to review comments article
Join call with coaching contact to discuss review results | Administrator
Make edits to and add any necessary documentation | Administrator
Upload your edited documentation to your scorecard and assign to locations | Administrator
Submit for your final review (20-25 business day turnaround) | Administrator |  |  | Submitting your WELL documentation article

## Celebrating - PR and employeete
Action item | Point person | Status | Notes/questions | Links/Resources
Review WELL PR materials | Administrator |  |  | Awards Guide Marketing Guidelines
Review Welcome to WELL toolkit | Administrator |  |  | Welcome to WELL toolkit
Host call with Communications, Marketing, and HR/employee engagement staff to discuss leveraging report results | Administrator
Send your WELL report to leadership and relevant departments, including for ESG reporting | Administrator
Create plan for WELL PR and employee engagement this year | PR rep/HR
Consider activities including: • Share info about WELL with employees or tenants • Issue WELL press release, social media campaign • Incorporate WELL into existing organizational materials, such as onboarding, benefits, etc. • Incorporate WELL into organizational report • Leverage Welcome to WELL toolkit for signage, email templates, feature facts • Using WELL in award applications (Best places to work, etc.) | PR rep/HR
Learn about ways other organizations have leveraged WELL for PR and engagement | PR rep/HR/Administrator |  |  | How WELL can help you build brand equity article Telling the WELL Core story article

## Integrating WELL into CSRESG re
Action item | Point person | Status | Notes/q's | Links/Resources
Learn about WELL's ESG alignment | ESG reporting lead |  |  | IWBI Investing for Health webpage
Review the WELL-ESG reporting guide | ESG reporting lead |  |  | WELL ESG reporting guide
Review the WELL-ESG reporting deck with client examples | ESG reporting lead |  |  | WELL-ESG client deck
Check out your WELL-UN SDGs impact report in your My Impact tab | ESG reporting lead |  |  | https://account.wellcertified.com/
Request a call with your coaching contact and your ESG reporting team for further support | Administrator
Learn about 12 Competencies for Measuring Health & Well-being for Human & Social Capital | ESG reporting lead |  |  | The 12 Competencies for Measuring Health & Well-being for Human & Social Capital
View more WELL-ESG resources in our knowledge base | ESG reporting lead |  |  | WELL-ESG resources

## Preparing for your WELL renewal
Action item | Point person | Status | Notes/q's | Links/Resources
(4 months in advance of your renewal date) Review your locations tab in your WELL dashboard to identify any property changes | Administrator |  |  | https://account.wellcertified.com/
(4 months in advance of your renewal date) Download your locations and note any changes/additions; send to your coaching contact | Administrator |  |  | https://account.wellcertified.com/
Receive and pay renewal invoice | Owner
Complete annual WELL survey, sent to you by IWBI | Administrator and Owner

## Setting your annual WELL goals
Action item | Point person | Status | Notes/q's | Links/Resources
Hold a kick off call for the year with your team and WELL coaching contact | Administrator
Update your goals module | Administrator
Update your Team tab in your WELL dashboard | Administrator |  |  | Add, modify or remove team members in the WELL project dashboard
Set achievement targets for the year | Administrator
Identify targeted date for your first review submission | Administrator |  |  | How to update your documentation submission date
Brief your stakeholders and leadership about your WELL goals and plan for the year | Administrator